## Slide 1: Project Planning
1. Purpose :
The Project Planning Phase breaks the ComicCraft project into clear, manageable milestones and activities.
It defines what will be done, in what order, and how progress will be tracked — turning the design blueprint into an actionable execution plan.
2. Project Milestones and ActivitiesMilestone :
1: Model Selection and Architecture:
Activity1.1 – Research and select the appropriate generative AI model.
Activity 1.2 – Define the architecture of the application.
Activity 1.3 – Set up the development environment.
Milestone 2: Core Functionalities Development :
Activity 2.1 – Develop the core functionalities (outline, story, and image generation).
Activity 2.2 – Implement the FastAPI backend to manage routing and user input processing.

## Slide 2
Milestone 3: routes.py Development :
Activity 3.1 – Write the main application logic in routes.py.
Milestone 4: Frontend Development :
Activity 4.1 – Design and develop the user interface.
Activity 4.2 – Create dynamic templates with FastAPI's Jinja2.
Milestone 5: Deployment :
Activity 5.1 – Prepare the application for local deployment.
Activity 5.2 – Test and verify local deployment.
3. Execution Sequence :
The milestones are executed in the following order, as each one builds on the outputs of the previous:
Model Selection and Architecture → establishes the AI models and system design.
Core Functionalities Development → builds the generation logic (outline, story, image).
routes.py Development → connects functionalities to accessible endpoints.
Frontend Development → builds the interface for users to interact with the system.

## Slide 3: Deployment → prepares and verifies the working application.
4.Resource Planning :
Development tools: Python, FastAPI, Uvicorn, Jinja2.
Jinja2AI services: Google Gemini API (Flash and Pro), Hugging Face Diffusers (Stable Diffusion).
Supporting libraries: FPDF, Pillow, python-multipart, accelerate.
Environment: Python virtual environment (comiccraft-env) for dependency isolation.
5.Tracking and Milestone Completion Criteria :
Milestone 1 is complete when the AI models are finalized and the architecture is documented.
Milestone 2 is complete when outline, story, and image generation functions work independently.
Milestone 3 is complete when all routes are defined and correctly linked to backend functions.
Milestone 4 is complete when the UI can capture input and render the comic preview.
Milestone 5 is complete when the application runs locally and passes basic testing.
6. Conclusion :
This planning phase organizes the ComicCraft project into five sequential milestones, each with clearly defined activities and completion criteria. This structured plan ensures steady progress from initial architecture decisions through to a fully functional, locally deployed application, and directly guides the work carried out in the Project Development phase.